## Sheet1
Category | Feature | Description | Complexity | Priority | Status | Planned Version | Dependency | Risk Level | Notes
Navigation Core | Core NavigationService API | Maintain SwitchPage / SwitchTransient entrypoints for type-based navigation. | Medium | High | Done | v1 |  | Medium
Navigation Core | Type-based navigation overloads | Support navigation by Type (non-generic) for dynamic scenarios. | Low | Medium | Done | v1 |  | Medium
Navigation Core | NavigationArgs payload model | Standard payload object for passing data between pages. | Low | High | Done | v1 |  | Medium
Navigation Core | UseCache flag honoring | Ensure UseCache controls whether PageRegistry.Resolve or CreateNew is used. | Low | High | Done | v1 |  | Medium
Navigation Core | Reentrancy guard _isNavigating | Prevent concurrent navigation calls from conflicting. | Medium | High | Done | v1 |  | Medium
Navigation Core | Host initialization guard | Throw clear error if Initialize was not called before navigation. | Low | High | Done | v1 |  | Medium
Navigation Core | CurrentChanged event | Fire when Current page instance changes successfully. | Low | Medium | Done | v1 |  | Medium
Navigation Core | Navigating / Navigated events | Lifecycle events before and after navigation, including payload info. | Medium | High | Done | v1 |  | Medium
Navigation Core | NavigationFailed event | Centralized failure callback with Exception for logging/UI. | Medium | High | Done | v1 |  | Medium
Navigation Core | GoHomeAsync helper | Convenience method to navigate to timeout/home target. | Low | Medium | Done | v1 |  | Medium
Navigation Core | Guard against null timeout target | Avoid exceptions when no timeout home page is registered. | Low | Medium | Done | v1 |  | Medium
Navigation Core | Allow custom navigation strategies | Design extension point to plug alternative navigation logic if needed. | High | Low | Not Started | v3 |  | High | Future extension seam.
History & State | PageHistoryEntry model | Lightweight record of visited page instance and timestamp. | Low | Medium | Done | v1 |  | Medium
History & State | Back/forward stacks | Maintain Back/Forward stacks of PageHistoryEntry. | Medium | High | Done | v1 |  | Medium
History & State | Record() API | Push current page into back stack and clear forward stack. | Low | High | Done | v1 |  | Medium
History & State | GoBackAsync | Navigate to previous page using history stack. | Medium | High | Done | v1 |  | Medium
History & State | GoForwardAsync | Navigate forward if available in history. | Medium | Medium | Done | v1 |  | Medium
History & State | HistoryChanged event | Event fired whenever history stacks change. | Low | Medium | Done | v1 |  | Medium
History & State | Expose HistoryBack/HistoryForward enumeration | Allow listing history stacks for debug UI. | Low | Medium | Done | v1 |  | Medium
History & State | Optional history recording suppression | Allow special navigations to skip being added to history. | Low | Medium | Done | v1 |  | Medium
History & State | Session restore concept design | Plan how the last page could be restored across app restart. | Medium | Medium | Not Started | v2 |  | Medium | Design only; implementation deferred.
History & State | Persisted history (disk) | Optional persistence of navigation history for long-running sessions. | High | Low | Not Started | v3 |  | High
Timeout & Behavior Logic | TimeoutService core | Central service using ITimerAdapter to fire TimeoutReached. | Medium | High | Done | v1 |  | Medium
Timeout & Behavior Logic | TimeoutBehavior enum | Default / OverrideHome / IgnoreTimeout per page. | Low | High | Done | v1 |  | Medium
Timeout & Behavior Logic | State tracking in TimeoutService | Track Running / Paused / Uninitialized etc. | Low | Medium | Done | v1 |  | Medium
Timeout & Behavior Logic | Reset hook for user interaction | Connect TimeoutService.Reset to click events via EventDispatcher. | Medium | High | Done | v1 |  | Medium
Timeout & Behavior Logic | Pause / Continue APIs | Allow pausing timeout during modal flows. | Low | High | Done | v1 |  | Medium
Timeout & Behavior Logic | OnTimeout handler in NavigationService | Navigation logic when timeout occurs, including OverrideHome. | Medium | High | Done | v1 |  | Medium
Timeout & Behavior Logic | Expose SecondsRemaining | Property to show remaining time to UI/debug. | Low | Medium | Done | v1 |  | Medium
Timeout & Behavior Logic | Adaptive timeout design | Define strategy for timeouts that depend on page or user state. | Medium | Low | Not Started | v2 |  | Medium
Timeout & Behavior Logic | Per-page timeout override settings | Option to define custom timeout durations per page. | Medium | Medium | Not Started | v2 |  | Medium
Dialogs & Overlays | IPageMask abstraction | Core abstraction to show/hide loading or blocking overlays. | Low | High | Done | v1 |  | Medium
Dialogs & Overlays | PageMaskService | Small facade to show/hide mask from NavigationService. | Low | High | Done | v1 |  | Medium
Dialogs & Overlays | Basic WinForms PageMask adapter | Panel overlay implementation for WinForms host. | Medium | High | In Progress | v1 |  | Medium
Dialogs & Overlays | Basic WPF PageMask adapter | Grid overlay implementation for WPF host. | Medium | High | In Progress | v1 |  | Medium
Dialogs & Overlays | Mask text support | Support showing 'Loading...' or custom text on mask. | Low | Medium | Done | v1 |  | Medium
Dialogs & Overlays | Blocking interaction with mask | Ensure interaction blocker disables underlying content while mask is visible. | Medium | High | In Progress | v1 |  | Medium
Dialogs & Overlays | Non-blocking toast-like notification concept | Define future model for small non-modal info popups. | Low | Low | Not Started | v2 |  | Low
Dialogs & Overlays | Central dialog abstraction (future) | High-level IChildWindow/dialog API for confirmation and alerts. | High | Medium | Not Started | v2 |  | High | Depends on IChildWindow design.
Subwindows & Child Windows | IChildWindow abstraction | Base contract for child/subwindow concept. | Medium | Medium | Not Started | v2 |  | Medium
Subwindows & Child Windows | ChildWindowService design | Internal manager for open child windows per host. | High | Medium | Not Started | v2 |  | High
Subwindows & Child Windows | Modal vs non-modal child windows rules | Define how child windows behave regarding navigation & timeout. | High | Medium | Not Started | v2 |  | High
Subwindows & Child Windows | Lock interaction while modal child open | Use IInteractionBlocker to block background while modal dialog shown. | Medium | High | Not Started | v2 | IChildWindow abstraction | Medium
Subwindows & Child Windows | Close propagation semantics | Clarify what happens when parent page closes while child still open. | Medium | Medium | Not Started | v2 |  | Medium
Subwindows & Child Windows | Integration with history | Decide if child windows affect navigation history or are separate. | High | Low | Not Started | v3 |  | High
Animation Layer | Transition hook design | Add extension points to plug animations before/after page attach. | High | Medium | Not Started | v2 |  | Medium
Animation Layer | Simple fade transition | Optional fade-in/fade-out between pages. | Medium | Medium | Not Started | v2 | Transition hook design | Medium
Animation Layer | Slide transition (left/right) | Slide pages in/out for navigation gestures. | Medium | Low | Not Started | v2 | Transition hook design | Medium
Animation Layer | Configurable transition duration | Allow per-page or global animation duration settings. | Low | Low | Not Started | v2 | Transition hook design | Low
Animation Layer | Cancelable transitions | Allow navigation cancellation if a new navigation is requested mid-transition. | High | Medium | Not Started | v3 | Transition hook design | High
Animation Layer | Pluggable easing functions | Support custom easing curves (linear, cubic, bounce, etc.). | Medium | Low | Not Started | v3 |  | Medium
Data & Integration | HTTP client wrapper | Simple HttpClient-based helper to call external APIs. | Medium | Medium | Not Started | v1 |  | Low
Data & Integration | PokéAPI integration | Fetch and display Pokémon list and details. | Medium | Medium | Not Started | v1 | HTTP client wrapper | Low
Data & Integration | OpenLibrary integration | Search books and display results with paging. | Medium | Medium | Not Started | v1 | HTTP client wrapper | Low
Data & Integration | SpaceX launches browser | Show recent launches and navigate to detail pages. | Medium | Medium | Not Started | v1 | HTTP client wrapper | Low
Data & Integration | SQLite local cache | Persist API data locally to test cache + offline scenarios. | High | High | Not Started | v1 |  | Medium
Data & Integration | Data-driven demo pages | Dedicated sample pages to stress NavigationService with real data. | Medium | High | Not Started | v1 | HTTP client wrapper; SQLite local cache | Medium
DX Tooling | PageLoggerService | In-memory list of navigation entries. | Low | High | Done | v1 |  | Medium
DX Tooling | PageLogger file logging | Thread-safe file logger for registry/navigation messages. | Medium | High | Done | v1 |  | Medium
DX Tooling | Configurable log file path | Allow configuring log path at startup. | Low | Medium | Done | v1 |  | Medium
DX Tooling | Log categories (Registry/Navigation/Timeout) | Basic log categorization by area. | Medium | Medium | In Progress | v1 |  | Medium
DX Tooling | Logger verbosity flags | Turn on/off debug/verbose logs for specific subsystems. | Medium | Medium | Not Started | v1 |  | Low
DX Tooling | Debug page in demo app | Page displaying history, timeout state, and recent logs. | Medium | Medium | Not Started | v1 |  | Low
DX Tooling | Design-time tools improvements | Utilities like IsInDesignMode to avoid running runtime code at design time. | Low | Medium | In Progress | v1 |  | Medium
Platform Adapters | IPlatformAdapter abstraction | Unified interface to create host, mask, events, timer, blockers. | Medium | High | Done | v1 |  | Medium
Platform Adapters | PlatformRegistry | Registry to manage available platform adapters and resolve based on host. | Medium | High | Done | v1 |  | Medium
Platform Adapters | WinForms adapter (host/mask/events/blocker/timer) | Full implementation of IPlatformAdapter for WinForms. | High | High | In Progress | v1 |  | Medium
Platform Adapters | WPF adapter (host/mask/events/blocker/timer) | Full implementation of IPlatformAdapter for WPF. | High | High | In Progress | v1 |  | Medium
Platform Adapters | Guarded CanHandle logic | Robust host type checking to avoid incorrect adapter resolution. | Low | Medium | Done | v1 |  | Medium
Platform Adapters | Error messages when no adapter found | Descriptive NotSupportedException when host type unsupported. | Low | Medium | Done | v1 |  | Medium
Platform Adapters | IMovableAdapter design (optional) | Optional abstraction for movable child windows. | Medium | Low | Not Started | v2 |  | Low
Platform Adapters | Consider MAUI/Avalonia adapter spike | Research feasibility for future cross-platform adapters. | High | Low | Not Started | v3 |  | High | Research only.
Performance & Memory | Cache policy enforcement | Ensure PageCachePolicy modes behave as documented. | Medium | High | Done | v1 |  | Medium
Performance & Memory | WeakSingleton semantics | ReleaseResources called but instance held for reuse. | Medium | Medium | Done | v1 |  | Medium
Performance & Memory | StrongSingleton semantics | Instance preserved with no ReleaseResources call by default. | Medium | Medium | Done | v1 |  | Medium
Performance & Memory | Stackable pages with OnDetach POP | Stack push/pop logic integrated with page detach events. | High | High | Done | v1 |  | Medium
Performance & Memory | Avoid double-dispose on pages | Ensure CleanupPageAsync does not dispose cached singleton pages. | Medium | High | Done | v1 |  | Medium
Performance & Memory | Event detach on navigation | Ensure all timeout click events are detached from old page. | Medium | High | Done | v1 |  | Medium
Performance & Memory | Review leaks in EventDispatcher | Check attached event tracking to avoid leaks. | Medium | High | In Progress | v1 |  | High
Performance & Memory | Optional weak-event adapter prototype | Experimental weak event dispatcher if needed. | High | Low | Not Started | v3 |  | High
Performance & Memory | Stress test navigation with many pages | Simulate high churn to validate GC and event cleanup. | Medium | Medium | Not Started | v1 |  | Medium
Experimental & Future | Middleware-like pipeline around navigation | Concept of pre-/post-navigation filters. | High | Medium | Not Started | v3 |  | High
Experimental & Future | Navigation guards (can/cannot navigate) | Predicate-based blocking of navigation under certain conditions. | High | Medium | Not Started | v2 |  | High
Experimental & Future | Deep linking prototype | Ability to navigate by token/URI representing full state. | High | Medium | Not Started | v3 |  | High
Experimental & Future | Multi-host support | Conceptual support for multiple active hosts. | High | Low | Not Started | Future |  | High
Experimental & Future | Plugin-based page discovery | Load pages from external assemblies dynamically. | High | Low | Not Started | Future |  | High